Bit-By-Bit Academy

Data Governance and Data Flow Audit

Findings Report and Action Plan

Completed by

Rhoda Report

Director of Technology

2026-05-14

Executive Summary

Assessment scope: 5 of 5 registered systems were audited in this session. Systems audited: Veracross (SIS), Google Workspace for Education Plus, Seesaw, Lightspeed Filter, Bark for Schools All registered systems were assessed.

Overall Grade: F · 5 systems audited 1 critical 2 high Systems by severity: 5 urgent

System Report Card Summary

Scores reflect controls in place across access, backup, data flow, vendor agreements, and data retention for each system.

| System | Grade | Score | Severity | Findings |
| --- | --- | --- | --- | --- |
| Veracross (SIS) | F | 0% | URGENT | 0 |
| Google Workspace for Education Plus | F | 0% | URGENT | 0 |
| Seesaw | F | 0% | URGENT | 0 |
| Lightspeed Filter | F | 0% | URGENT | 0 |
| Bark for Schools | F | 0% | URGENT | 0 |

Top Priorities

The highest-severity actions across all systems and school-wide findings, ordered by urgency. Assign an owner and deadline for each before this report is filed.

| Finding | System / Scope | Owner | Timing |
| --- | --- | --- | --- |
| No documented offboarding process for system access | School-Wide | HR / IT Director | Do within 30 days |
| No formal data governance policy | School-Wide | Head of School / IT Director | Do within 30 days |
| No documented data breach response plan | School-Wide | Head of School / IT Director | Do within 30 days |

School-Wide Governance

6 school-wide governance findings identified — see the School-Wide Findings section for detail and recommended actions.

Per-System Findings

One section per system. Findings are ordered by severity. Effort ratings: S=½ day · S+=1 day · M=3 days · M+=5 days · L=10 days.

Veracross (SIS)

Grade: F   Score: 0% (0/96 pts)   Status: URGENT

| Area | Score | Bar |
| --- | --- | --- |
| Access Control | 0% | ░░░░░░░░░░ |
| Backup & Recovery | 0% | ░░░░░░░░░░ |
| Data Flows | 0% | ░░░░░░░░░░ |
| Vendor & Contract | 0% | ░░░░░░░░░░ |
| Retention & Disposal | 0% | ░░░░░░░░░░ |

✓ All assessed controls appear to be in place.

Google Workspace for Education Plus

Grade: F   Score: 0% (0/96 pts)   Status: URGENT

| Area | Score | Bar |
| --- | --- | --- |
| Access Control | 0% | ░░░░░░░░░░ |
| Backup & Recovery | 0% | ░░░░░░░░░░ |
| Data Flows | 0% | ░░░░░░░░░░ |
| Vendor & Contract | 0% | ░░░░░░░░░░ |
| Retention & Disposal | 0% | ░░░░░░░░░░ |

✓ All assessed controls appear to be in place.

Seesaw

Grade: F   Score: 0% (0/96 pts)   Status: URGENT

| Area | Score | Bar |
| --- | --- | --- |
| Access Control | 0% | ░░░░░░░░░░ |
| Backup & Recovery | 0% | ░░░░░░░░░░ |
| Data Flows | 0% | ░░░░░░░░░░ |
| Vendor & Contract | 0% | ░░░░░░░░░░ |
| Retention & Disposal | 0% | ░░░░░░░░░░ |

✓ All assessed controls appear to be in place.

Lightspeed Filter

Grade: F   Score: 0% (0/96 pts)   Status: URGENT

| Area | Score | Bar |
| --- | --- | --- |
| Access Control | 0% | ░░░░░░░░░░ |
| Backup & Recovery | 0% | ░░░░░░░░░░ |
| Data Flows | 0% | ░░░░░░░░░░ |
| Vendor & Contract | 0% | ░░░░░░░░░░ |
| Retention & Disposal | 0% | ░░░░░░░░░░ |

✓ All assessed controls appear to be in place.

Bark for Schools

Grade: F   Score: 0% (0/96 pts)   Status: URGENT

| Area | Score | Bar |
| --- | --- | --- |
| Access Control | 0% | ░░░░░░░░░░ |
| Backup & Recovery | 0% | ░░░░░░░░░░ |
| Data Flows | 0% | ░░░░░░░░░░ |
| Vendor & Contract | 0% | ░░░░░░░░░░ |
| Retention & Disposal | 0% | ░░░░░░░░░░ |

✓ All assessed controls appear to be in place.

School-Wide Governance Findings

These findings apply across all systems rather than to any single platform. They represent policy, process, and governance gaps that affect the school's overall data protection posture.

[CRITICAL]  No documented offboarding process for system access

The school does not have a documented checklist for revoking system access when staff members leave. Former staff accounts found in the per-system worksheets are the direct result of this gap. An informal process that relies on memory will always have exceptions.

Action: Create an offboarding checklist that names every system and requires sign-off on access revocation for each. Run it on the last day of employment for every departure. Assign HR as the trigger and IT as the executor. Review the checklist annually to add newly adopted systems. Owner: HR / IT Director · Do within 30 days · Medium (3 days)

[HIGH]  No formal data governance policy

The school does not have a formally adopted written data governance or data privacy policy. Without this policy, there is no authoritative reference for how data should be handled, stored, or deleted — and no basis for accountability when things go wrong.

Action: Draft and formally adopt a data governance policy. Keep the initial version short and practical — a one-page policy with clear ownership is more effective than a lengthy document no one reads. Review it annually and assign a named owner. Owner: Head of School / IT Director · Do within 30 days · Medium (3 days)

[HIGH]  No documented data breach response plan

The school does not have a written plan for responding to a data breach. Florida FIPA requires breach notification to affected individuals within 30 days — extremely difficult without a pre-existing response plan that names who does what and in what order.

Action: Create a breach response plan. It does not need to be long — a one-page flowchart naming who does what and within what timeframes is sufficient. Test it annually and update it when key staff change. Owner: Head of School / IT Director · Do within 30 days · Medium (3 days)

[MEDIUM]  No master data register exists

The school does not maintain a master register of systems, what data they hold, and how long it is kept. Without a register, the school cannot quickly answer basic compliance questions about where student data lives.

Action: Use the per-system worksheets from this audit as the foundation for a master data register. Publish it on a shared intranet page — one section per system with data categories, retention periods, vendor name, and an owner contact. Assign someone to review it annually. Owner: IT Director · Do within 90 days · Medium (3 days)

[MEDIUM]  No regular staff data privacy training

Staff are not trained on data privacy and responsible data handling on a regular schedule. Staff are a primary vector for data incidents — phishing, accidental sharing, and mis-addressed emails are all preventable with training.

Action: Schedule annual data privacy training for all staff. A 30-minute session covering phishing, data sharing rules, and who to call if something goes wrong is a strong baseline. Document attendance. Owner: HR / IT Director · Do within 90 days · Medium (3 days)

[MEDIUM]  No data retention schedule

The school does not have a written data retention schedule defining how long each category of data must be kept. Florida law sets minimum retention periods for student, health, and financial records.

Action: Create a data retention schedule aligned to Florida requirements. Start with the highest-risk categories: student records, health records, HR files, and financial data. Assign a named owner and review annually. Owner: IT Director / Business Office · Do within 90 days · Substantial (5 days)

Action Plan

All recommended actions grouped by timing bucket, then by area. Each action lists the suggested owner role and estimated effort. Assign a named individual and a target date before this report is filed.

Immediate — Do Within 30 Days

Critical and high-severity findings. Assign an owner and start date today.

| Action | System | Owner | Effort | Severity |
| --- | --- | --- | --- | --- |
| Create an offboarding checklist that names every system and requires sign-off on access revocation for each. Run it on the last day of employment for every departure. Assign HR as the trigger and IT as the executor. Review the checklist annually to add newly adopted systems. | School-Wide | HR / IT Director | Medium (3 days) | CRITICAL |
| Draft and formally adopt a data governance policy. Keep the initial version short and practical — a one-page policy with clear ownership is more effective than a lengthy document no one reads. Review it annually and assign a named owner. | School-Wide | Head of School / IT Director | Medium (3 days) | HIGH |
| Create a breach response plan. It does not need to be long — a one-page flowchart naming who does what and within what timeframes is sufficient. Test it annually and update it when key staff change. | School-Wide | Head of School / IT Director | Medium (3 days) | HIGH |

Near-Term — Do Within 90 Days

Medium-severity findings. Schedule these before the end of next quarter.

| Action | System | Owner | Effort | Severity |
| --- | --- | --- | --- | --- |
| Create a data retention schedule aligned to Florida requirements. Start with the highest-risk categories: student records, health records, HR files, and financial data. Assign a named owner and review annually. | School-Wide | IT Director / Business Office | Substantial (5 days) | MEDIUM |
| Use the per-system worksheets from this audit as the foundation for a master data register. Publish it on a shared intranet page — one section per system with data categories, retention periods, vendor name, and an owner contact. Assign someone to review it annually. | School-Wide | IT Director | Medium (3 days) | MEDIUM |
| Schedule annual data privacy training for all staff. A 30-minute session covering phishing, data sharing rules, and who to call if something goes wrong is a strong baseline. Document attendance. | School-Wide | HR / IT Director | Medium (3 days) | MEDIUM |

Phased Remediation Timeline

All recommended actions grouped by phase, ordered by severity then effort. Effort ratings: S=½ day · S+=1 day · M=3 days · M+=5 days · L=10 days.

Phase 1 — Immediate Actions · 14 May 2026 → 23 May 2026

| Action | System / Area | Effort | Severity |
| --- | --- | --- | --- |
| Create an offboarding checklist that names every system and requires sign-off on access revocation for each. Run it on the last day of employment for every departure. Assign HR as the trigger and IT as the executor. Review the checklist annually to add newly adopted systems. | No documented offboarding process for system access | Medium (3 days) | URGENT |
| Draft and formally adopt a data governance policy. Keep the initial version short and practical — a one-page policy with clear ownership is more effective than a lengthy document no one reads. Review it annually and assign a named owner. | No formal data governance policy | Medium (3 days) | CONCERN |
| Create a breach response plan. It does not need to be long — a one-page flowchart naming who does what and within what timeframes is sufficient. Test it annually and update it when key staff change. | No documented data breach response plan | Medium (3 days) | CONCERN |

⚡ ⚡ Re-assessment recommended: with 3 immediate actions addressed, a follow-up review after Phase 1 completion will confirm risk reduction and may adjust priorities for subsequent phases.

Phase 2 — Within 30 Days · 28 May 2026 → 08 Jun 2026

| Action | System / Area | Effort | Severity |
| --- | --- | --- | --- |
| Create a data retention schedule aligned to Florida requirements. Start with the highest-risk categories: student records, health records, HR files, and financial data. Assign a named owner and review annually. | No data retention schedule | Substantial (5 days) | WATCH |
| Use the per-system worksheets from this audit as the foundation for a master data register. Publish it on a shared intranet page — one section per system with data categories, retention periods, vendor name, and an owner contact. Assign someone to review it annually. | No master data register exists | Medium (3 days) | WATCH |
| Schedule annual data privacy training for all staff. A 30-minute session covering phishing, data sharing rules, and who to call if something goes wrong is a strong baseline. Document attendance. | No regular staff data privacy training | Medium (3 days) | WATCH |

Getting Started — Building a Governance Rhythm

The findings in this report can feel overwhelming when taken all at once. Research on K-12 data governance shows that the most effective approach is to start small: assign ownership, build one simple routine, and let it grow. The checklist and monthly ritual below are designed for schools at the beginning of that journey.

Your First Five Steps

1. Write a one-sentence data governance vision and share it with leadership — e.g. 'Our school protects student data by knowing what we hold, who can access it, and how long we keep it.' 2. Appoint a named Data Governance Owner (primary) and a backup. This does not require a new hire — assign it to the IT Director or a senior administrator and document it in writing. 3. Use the Action Plan in this report to identify your top 3 actions. Assign each one a named owner and a deadline before this report is filed away. 4. Schedule a recurring 15-minute monthly governance check-in with IT and at least one member of leadership. Keep a short written record of what was discussed and decided each month. 5. Create a one-page data register from this audit's per-system worksheets and publish it on a shared drive. One row per system: data held, vendor, retention period, and owner contact.

The 15-Minute Monthly Governance Check-In

Schedule a recurring 15-minute meeting with IT and at least one member of leadership. The agenda is the same every month — keep it short, keep a written record, and rotate the host so it survives staff turnover.

Monthly agenda: ✓ Review one open finding from the Action Plan — confirm whether the action was taken and update the record. ✓ Ask: has any new tool or vendor been adopted since last month? If yes, run the vendor approval checklist before data is shared. ✓ Check whether any staff have joined or left — confirm offboarding was completed for all departures. ✓ Note any policy or regulatory updates (e.g. state rule changes, new data categories) that may affect how the school handles data. ✓ Record the meeting: what was discussed, what was agreed, who owns it, and when it will be checked again.

Appendix — Raw Response Log

Complete record of all answers submitted for each system worksheet, with question prompts for context. Questions with no answer are omitted.

1. Veracross (SIS)

| Question ID | Question | Status | Answer |
| --- | --- | --- | --- |
| _SYS.1.1 |  | answered | Partial — list available but may be incomplete |
| _SYS.1.1a |  | answered | unknown |
| _SYS.1.2 |  | answered | Role-based — different roles see different data |
| _SYS.1.2a |  | answered | yes |
| _SYS.1.3 |  | answered | Partial — available but not required |
| _SYS.1.4 |  | answered | yes |
| _SYS.1.5 |  | answered | Yes — logs exist but not reviewed regularly |
| _SYS.2.1 |  | answered | Yes — vendor manages the backup |
| _SYS.2.1a |  | answered | unknown |
| _SYS.2.1b |  | answered | no |
| _SYS.2.5v |  | answered | Informal plan — relies on memory or ad-hoc decisions |
| _SYS.3.1 |  | answered | Data enters Veracross via: (1) manual entry by the registrar and admissions team, (2) parent-submitted enrollment forms through the Veracross parent portal, (3) nightly sync from Google Workspace for |
| _SYS.3.2 |  | answered | Data leaves Veracross via: (1) rostering sync to Google Classroom (nightly), (2) rostering sync to Seesaw (manual export / upload), (3) reporting exports by the Head of School and Board, (4) transcrip |
| _SYS.3.2a |  | answered | Partial — some encrypted, some not |
| _SYS.3.3 |  | answered | yes |
| _SYS.3.3a |  | answered | Nightly Google Classroom roster sync via Veracross API connector — set up by former IT staff approx. 3 years ago. Still in active use. No review has been performed on the OAuth scopes granted. |
| _SYS.3.4 |  | answered | yes |
| _SYS.3.4a |  | answered | Transcripts are exported and emailed to external schools or colleges on request by the registrar. No written data sharing agreement governs these transfers beyond FERPA consent forms signed by parents |
| _SYS.3.5 |  | answered | Unknown |
| _SYS.4.1 |  | answered | Unknown |
| _SYS.4.4 |  | answered | No — not reviewed |
| _SYS.5.1 |  | answered | Student academic records (grades, transcripts, reports), Student behavioral records (discipline, incidents), Student health records (medical, counseling, nurse), Parent and family contact data, Admiss |
| _SYS.5.2 |  | answered | Academic records (transcripts, grades): permanent per Florida law. Health records: 7 years after student turns 18. Discipline records: 5 years. Family contact data: duration of enrollment plus 3 years |
| _SYS.5.3 |  | answered | No deletion process — data accumulates indefinitely |
| _SYS.ID.dept |  | answered | All departments — primary system of record for student data |
| _SYS.ID.name |  | answered | Veracross (SIS) |
| _SYS.ID.status |  | answered | Active — in regular use |
| _SYS.ID.vendor |  | answered | Veracross |

2. Google Workspace for Education Plus

| Question ID | Question | Status | Answer |
| --- | --- | --- | --- |
| _SYS.1.1 |  | answered | Yes — complete list available |
| _SYS.1.1a |  | answered | yes |
| _SYS.1.2 |  | answered | Role-based — different roles see different data |
| _SYS.1.2a |  | answered | no |
| _SYS.1.3 |  | answered | Partial — available but not required |
| _SYS.1.4 |  | answered | yes |
| _SYS.1.5 |  | answered | Yes — logs retained 90+ days and reviewed regularly |
| _SYS.2.1 |  | answered | Both — school and vendor both maintain copies |
| _SYS.2.1a |  | answered | yes |
| _SYS.2.2 |  | answered | Continuously (real-time replication) |
| _SYS.2.3 |  | answered | Never tested |
| _SYS.2.4 |  | answered | yes |
| _SYS.2.5 |  | answered | 4–24 hours |
| _SYS.3.1 |  | answered | Data enters Google Workspace via: (1) nightly roster sync from Veracross for class rosters and groups, (2) staff email and file creation, (3) student file submissions through Google Classroom, (4) ext |
| _SYS.3.2 |  | answered | Data leaves Google Workspace via: (1) email to external addresses, (2) Google Drive files shared externally via link, (3) Classroom roster sync to Seesaw, (4) Bark for Schools monitoring connection re |
| _SYS.3.2a |  | answered | Yes — all outbound transfers are encrypted |
| _SYS.3.3 |  | answered | yes |
| _SYS.3.3a |  | answered | 1. Veracross → Google Workspace (nightly OU/roster sync via API). Set up by previous IT staff. Still needed — drives class organization. 2. Bark for Schools → Google Workspace (OAuth connection scanni |
| _SYS.3.4 |  | answered | no |
| _SYS.3.5 |  | answered | Yes — sub-processors are named in the contract |
| _SYS.4.1 |  | answered | Yes — signed DPA on file |
| _SYS.4.2 |  | answered | Yes — timeframe not specified |
| _SYS.4.3 |  | answered | Yes — deletion required with written confirmation |
| _SYS.4.4 |  | answered | Yes — reviewed published documentation only |
| _SYS.5.1 |  | answered | Student academic records (grades, transcripts, reports), Parent and family contact data, Communications (email, messages, chat), Intellectual property (curriculum, assessments), Authentication credent |
| _SYS.5.2 |  | answered | Staff email and files: retain for duration of employment plus 7 years (HR standard). Student accounts: retained for duration of enrollment; student Drive files retained for 1 year post-graduation per |
| _SYS.5.3 |  | answered | Deletion occurs but is not documented |
| _SYS.ID.dept |  | answered | All departments — primary email, collaboration, and file storage platform |
| _SYS.ID.name |  | answered | Google Workspace for Education Plus |
| _SYS.ID.status |  | answered | Active — in regular use |
| _SYS.ID.vendor |  | answered | Google |

3. Seesaw

| Question ID | Question | Status | Answer |
| --- | --- | --- | --- |
| _SYS.1.1 |  | answered | Partial — list available but may be incomplete |
| _SYS.1.1a |  | answered | unknown |
| _SYS.1.2 |  | answered | Role-based — different roles see different data |
| _SYS.1.2a |  | answered | no |
| _SYS.1.3 |  | answered | No — not available or not enabled |
| _SYS.1.4 |  | answered | no |
| _SYS.1.4a |  | answered | no |
| _SYS.1.5 |  | answered | Unknown |
| _SYS.2.1 |  | answered | Yes — vendor manages the backup |
| _SYS.2.1a |  | answered | unknown |
| _SYS.2.1b |  | answered | no |
| _SYS.2.5v |  | answered | Informal plan — relies on memory or ad-hoc decisions |
| _SYS.3.1 |  | answered | Student rosters are uploaded manually from a Veracross CSV export at the start of each school year. Parent email addresses are entered manually by teachers or uploaded in the roster. |
| _SYS.3.2 |  | answered | Data leaves Seesaw via: (1) PDF portfolio exports downloaded by teachers and shared with parents, (2) parent access to the Seesaw Family app (direct push notifications and journal viewing), (3) no kno |
| _SYS.3.2a |  | answered | Partial — some encrypted, some not |
| _SYS.3.3 |  | answered | no |
| _SYS.3.4 |  | answered | no |
| _SYS.3.5 |  | answered | Unknown |
| _SYS.4.1 |  | answered | No agreement on file |
| _SYS.4.4 |  | answered | No — not reviewed |
| _SYS.5.1 |  | answered | Student academic records (grades, transcripts, reports), Parent and family contact data |
| _SYS.5.2 |  | answered | Student portfolio and work data: retention period not defined. Parent contact data: retained for duration of enrollment plus unknown period. Seesaw's data retention terms have not been reviewed. |
| _SYS.5.3 |  | answered | Unknown |
| _SYS.ID.dept |  | answered | Lower School (Kindergarten through Grade 2) |
| _SYS.ID.name |  | answered | Seesaw |
| _SYS.ID.status |  | answered | Active — in regular use |
| _SYS.ID.vendor |  | answered | Seesaw Learning, Inc. |

4. Lightspeed Filter

| Question ID | Question | Status | Answer |
| --- | --- | --- | --- |
| _SYS.1.1 |  | answered | Yes — complete list available |
| _SYS.1.1a |  | answered | no |
| _SYS.1.2 |  | answered | Role-based — different roles see different data |
| _SYS.1.2a |  | answered | no |
| _SYS.1.3 |  | answered | Partial — available but not required |
| _SYS.1.4 |  | answered | yes |
| _SYS.1.5 |  | answered | Yes — logs exist but not reviewed regularly |
| _SYS.2.1 |  | answered | Yes — vendor manages the backup |
| _SYS.2.1a |  | answered | unknown |
| _SYS.2.1b |  | answered | no |
| _SYS.2.5v |  | answered | No plan — school would be unable to operate without this system |
| _SYS.3.1 |  | answered | User and device data enters Lightspeed via Google Workspace directory sync. No other inbound data sources. |
| _SYS.3.2 |  | answered | Lightspeed does not push data outbound to other school systems. Browsing activity logs are available to admins and teachers within the Lightspeed console only. |
| _SYS.3.2a |  | answered | Yes — all outbound transfers are encrypted |
| _SYS.3.3 |  | answered | yes |
| _SYS.3.3a |  | answered | Google Workspace → Lightspeed (identity and OU sync for policy assignment). This is the only automated connection. Set up by current IT director in 2023. Still active and needed. |
| _SYS.3.4 |  | answered | no |
| _SYS.3.5 |  | answered | Unknown |
| _SYS.4.1 |  | answered | Yes — signed DPA on file |
| _SYS.4.2 |  | answered | Yes — timeframe not specified |
| _SYS.4.3 |  | answered | Yes — deletion required with written confirmation |
| _SYS.4.4 |  | answered | Yes — reviewed published documentation only |
| _SYS.5.1 |  | answered | Security and audit logs, Student academic records (grades, transcripts, reports) |
| _SYS.5.2 |  | answered | Browsing activity logs: retention period not formally defined by school policy. Lightspeed's default retention is unknown. This should be reviewed with the vendor. |
| _SYS.5.3 |  | answered | Vendor handles deletion — not confirmed |
| _SYS.ID.dept |  | answered | IT — student content filtering across all school-managed devices |
| _SYS.ID.name |  | answered | Lightspeed Filter |
| _SYS.ID.status |  | answered | Active — in regular use |
| _SYS.ID.vendor |  | answered | Lightspeed Systems |

5. Bark for Schools

| Question ID | Question | Status | Answer |
| --- | --- | --- | --- |
| _SYS.1.1 |  | answered | Partial — list available but may be incomplete |
| _SYS.1.1a |  | answered | no |
| _SYS.1.2 |  | answered | Role-based — different roles see different data |
| _SYS.1.2a |  | answered | no |
| _SYS.1.3 |  | answered | Partial — available but not required |
| _SYS.1.4 |  | answered | yes |
| _SYS.1.5 |  | answered | Unknown |
| _SYS.2.1 |  | answered | Yes — vendor manages the backup |
| _SYS.2.1a |  | answered | unknown |
| _SYS.2.1b |  | answered | no |
| _SYS.2.5v |  | answered | Informal plan — relies on memory or ad-hoc decisions |
| _SYS.3.1 |  | answered | Bark connects to student Google Workspace accounts via OAuth. It reads email, Drive activity metadata, and Google Chat messages for safety signal analysis. No other inbound data sources. |
| _SYS.3.2 |  | answered | Bark sends email and push notification alerts to designated school staff (IT director, Head Counselor) when safety signals are detected. Alert content includes excerpts of student communications. No o |
| _SYS.3.2a |  | answered | Yes — all outbound transfers are encrypted |
| _SYS.3.3 |  | answered | yes |
| _SYS.3.3a |  | answered | Google Workspace → Bark (OAuth connection reading student email, Drive, and Chat). Set up by current IT director in 2023. Active and needed. OAuth scopes should be reviewed annually — last reviewed at |
| _SYS.3.4 |  | answered | no |
| _SYS.3.5 |  | answered | Unknown |
| _SYS.4.1 |  | answered | Yes — signed DPA on file |
| _SYS.4.2 |  | answered | Yes — 72 hours or less |
| _SYS.4.3 |  | answered | Yes — deletion required with written confirmation |
| _SYS.4.4 |  | answered | Yes — reviewed published documentation only |
| _SYS.5.1 |  | answered | Student behavioral records (discipline, incidents), Communications (email, messages, chat) |
| _SYS.5.2 |  | answered | Alert records: retained within Bark for an unknown period. The school does not export alert records to a separate system. No retention schedule has been defined for Bark alert data. |
| _SYS.5.3 |  | answered | Vendor handles deletion — not confirmed |
| _SYS.ID.dept |  | answered | IT and School Counseling — student safety monitoring |
| _SYS.ID.name |  | answered | Bark for Schools |
| _SYS.ID.status |  | answered | Active — in regular use |
| _SYS.ID.vendor |  | answered | Bark Technologies, Inc. |